# Keeping the UConn Program Running

Program Administrator · Standard Operating Procedure · Version 0.1 (draft) · Reviewed May 2026

Draft — example content pending review and sign-off. Do not use for training until approved.

Proposed task set — confirm with Vanessa. The admin role’s exact responsibilities are not yet finalized. The tasks below are a starting proposal drawn from the pilot’s operational needs; treat them as a draft to react to, not a settled scope.

As the administrator, you keep five things current so the clinical team can focus on participants: staff readiness, system access, materials, UConn data requests, and subcontractor onboarding.

## Who this is for and what it covers

What this role covers, and where its boundaries are (proposed).

| For | Cena’s program administrator(s) supporting the UConn Health pilot. |
| --- | --- |
| Covers | Staff training and credential tracking, system-access provisioning, materials-distribution tracking, consent-form digitization and storage, UConn data-export requests, and subcontractor onboarding. |
| Does not cover | Clinical work (Registered Dietitian), participant care coordination (Care Coordinator), or participant enrollment intake (Enrollment & Onboarding SOP). |

## Your standing responsibilities

What keeps the program compliant and running.

- Track staff training and credentials. In the staff training tracker — every staff member and MPH student. Result: everyone who touches participant data has current CITI / IRB training on file. Note: someone without current training must not be given access to participant data.

- Give each person the system access their role needs. In the system admin settings. Result: each person has the access their role requires under the IRB protocol — and no more than that. The cap protects participant data.

- Track materials distribution. In the materials-distribution tracker. Result: a record of which educational materials and recipe booklets (English / Spanish) reached which participant.

- Send UConn the data they requested. Through the data-export process. Result: requested data delivered in a format UConn can open without Cena’s tools (a non-proprietary format) within 15 days. Note: the 15-day turnaround is a contract requirement — start promptly when a request comes in.

- Onboard subcontractors with signed BAAs. Through the subcontractor onboarding checklist. Result: kitchen, delivery, and clinical subcontractors are onboarded with a signed BAA before they handle any participant data.

- Digitize and store signed consent forms. Scan paper consent forms signed at the in-person first visit to PDF; file the PDF on the participant record in Athena the same day the form is signed. Result: every active participant has a signed-consent PDF on their record; no paper consents persist outside Athena. Note: this supersedes the earlier “locked-cabinet paper copies” approach. The signed PDF is the only canonical consent artifact going forward. [CONFIRM build state — consent-PDF upload workflow in admin app] [NEEDS VANESSA CONFIRMATION — digitization owner: admin role or shared with care coordinator]

## Access requests — give only when training is current

The one branch that comes up often — and the gate that protects participant data.

Their CITI / IRB training is current — Give the access their role requires under the IRB protocol.

Their training is missing or expired — Hold access until training is complete. Participant-data access requires current training — no exceptions.

## Keep current — the standing checks

The standing checks, condensed.

- Every staff member and MPH student has current CITI / IRB training

- System access matches each person’s role under the IRB protocol

- Materials distribution is logged per participant

- Any open UConn data-export request is on track for the 15-day window

- Every active subcontractor has a signed BAA on file

- Every active participant has a signed-consent PDF filed in Athena

## Terms used here

Plain-language definitions.

CITI / IRB training

The required human-subjects research training everyone must complete before working with participant data.

IRB protocol

The study’s approved rules for how the research is run, including who may see what data.

BAA

Business Associate Agreement — the contract a partner signs before they’re allowed to handle participant data.

Role-based access

Giving each person only the system access their job needs — nothing more.

Non-proprietary format

A common, openable file type (not locked to one vendor’s software) that UConn can use without Cena’s tools.

Signed-consent PDF

The participant’s paper IRB-consent form, signed at the in-person first visit and scanned to PDF the same day. The PDF is the canonical consent artifact, filed on the participant record in Athena.

## Approval status

Approved for use only when the scope is confirmed and the gates are signed.

Sign-off

⏳ Scope confirmed — Vanessa Sena (admin task set)

⏳ Operationally true — Vanessa Sena

⏳ Signed off — Director of Clinical Ops

Awaiting scope confirmation + sign-off — draft · Version 0.1